Learning from the Lives and deaths of people with a Learning Disability (LeDeR) – Early Identification of Deterioration in Supported Living Settings

AHSN’s (Academic Health Science Network) and ADASS (Association of Directors of Adult Social Services)
 Detecting Physical Deterioration in Supported Living Settings: Midlands Regional Pilot

1.0 The Memorandum

This ‘Ways of Working’ document (‘WOWWOW’) sets out the terms and understanding between and is entered into by the following organisations:

- East Midlands AHSN

- West Midlands AHSN

- East Midlands ADASS

- West Midlands ADASS

- NHS England and Improvement (Midlands Region)

- NHS England and Improvement National LeDeR Programme

For the purposes of this WOWWOW hereinafter referred to collectively as ‘the parties.’

The WOWWOW reflects an intent between the parties to work together on a collaborative project entitled, ‘AHSN’s and ADASS Detecting Physical Deterioration in Supported Living Settings: Midlands Regional Pilot.'’

All other arrangements i.e. financial, data sharing etc. sit outside this document, and will be covered by separate agreements where relevant.

This WOWWOW describes the initial relationship between the parties listed to facilitate effective cooperation, collaboration and alignment in relation to the ‘AHSN’s and ADASS.
Detecting Physical Deterioration in Supported Living Settings: Midlands Regional Pilot

The parties to this WOWWOW will be required to provide information to facilitate the planned AHSN delivery, and vice versa. Therefore, there are interdependencies between the parties named within the WOWWOW.

2.0 Background

Extensive work is underway in local areas across England to improve the management of deterioration amongst people with a Learning Disability living in care homes. However, this cohort only captures 11% of people with a Learning Disability, leaving those with potentially less social care support at a higher level of vulnerability to poorly managed deterioration.

Supported living is varied in terms of the level of support provided, with some people living relatively independently in their own homes with a few hours of outreach support per week, whilst others live either alone or with other service users with 24hr staff support.

The LeDeR programme and longstanding reports provide evidence that the signs of health deterioration are not always detected promptly by carers and furthermore that concerns expressed by carers to health professionals are not always taken seriously or responded to in ways that maximise the potential for good health outcomes. As such, people with a Learning Disability die prematurely with conditions that could have been prevented or amenable to treatment, with commonly occurring causes of death including pneumonia, aspiration pneumonia, sepsis, ischaemic heart disease and epilepsy. There are also a concerning number of deaths due to constipation.

The aim of this work is to undertake an at-pace pilot of an approach to managing deterioration amongst people with a learning disability living in supported living settings. At the end of the pilot there should be an evidence-based product/methodology/tool that can be scaled up and considered for roll out nationally. (i.e. a clearly defined, replicable model with a “how-to” guide to reduce unnecessary duplication of work should it be rolled out across England).

See Appendix A – For further background information and project brief from LeDeR.

3.0 Commitments of the Parties under this WOWWOW

The parties confirm their intent to work collaboratively on the ‘AHSN’s and ADASS early identification of deterioration through Supported Living Services Midlands Regional Pilot’ project described in Appendix A.

The relationships and obligations between individual parties, the agreement of detailed project plans and corresponding deliverables, timescales and associated finances will be constituted in this agreement between the relevant parties.

The timeline for these agreements to be in place is by 30th April 2021.

4.0 Agreed scope and limitations

The project requires an at pace action learning approach, utilising Quality Improvement methodology to test approaches to better manage deterioration among people with a learning disability receiving care through supported living services.

The interventions tested need to be evidence based and amenable to QI methodology approaches to support implementation.

The interventions tested will be aligned to the Prevention Identification Escalation and Response (PIER) framework (Appendix B) outlined by the National Patient Safety Team and will seek to explore all four elements of PIER.

The broad variance of individual needs of service users, and the range of different supported living care models, will limit the ability to test all interventions in all scenarios.

Testing will focus on acceptability, applicability and suitability of tools within areas deployed.

Testing will focus on the priority areas identified within the LeDeR Annual Report for 2020/21 and 2021/22. Deterioration from infections and constipation will be a primary care of focus (including sepsis, pneumonia and aspiration pneumonia).

The focus on acute deterioration reflects the short delivery period of the project and the need to measure impact during rapid tests of change. Longer term testing and measurement would be required for interventions relating to Long Term Conditions.

Testing will seek to better understand the relationship between deterioration from acute conditions and the presence of a range of long-term conditions which could include dementia, cancer, CVD and severe mental illness.

Whilst epilepsy was identified as a priority area within LeDeR, if is recognised that the interventions for this condition are beyond the scope of this project.

Engagement of health and care systems to support local testing may be impacted negatively as systems manage the ongoing COVID 19 pandemic, and / or enter a period of pandemic recovery.

To mitigate this the AHSNs will focus work with willing systems who respond positively to testing proposed interventions.

Different interventions may be tested in different locations/systems.

Test sites will reflect both urban and rural care systems, and span both East and West Midlands.

Testing will be conducted within a place-based approach (rather than following provider services) to allow for whole system testing – recognising that the response to escalation crosses provider responsibilities within health and social care services.

5.0 AHSN support for the project and key deliverables

- EMAHSN and WMAHSN will utilise allocated resources to facilitate the project within the East and West Midlands health and social care economies.

- AHSN’s will work with project partners to lead an at-pace pilot of an approach to managing deterioration amongst people with a learning disability living in supported living settings

- AHSNs will support this local project utilising skills and experience they have within the Patient Safety Collaborative, this project is not part of the work commissioned nationally as part of the National Patient Safety improvement programmes.

- To facilitate rapid mobilization East Midlands AHSN will procure a dedicated Senior Programme manager with experience of the national deterioration safety improvement agenda to lead the programme delivery for the first 6 month of the programme. This function will be recruited to for the remainder of the project via a secondment or fixed term post.

- The AHSNs will ensure there are robust risk management processes in place to escalation and manage risk for the programme of work.  All project sponsors will be kept informed of the key risks and mitigating actions in pace to manage them.

- The Programme Manager function will be funded with an additional £25,000 funding from EMAHSN to deliver aligned innovation exchange activities exploring the role of digital and AI solutions relating to the project objectives.

- EMAHSN will procure the services of a GP Fellow to provide 2 sessions of time to the project per week. The GP fellow will provide clinical advice and support to pilot sites, support the communication and engagement at the primary care interface, and support the evaluation of evidence and production of a literature review.

AHSN will deliver in 4 main phases:

- Pre-Diagnostic Phase

  - Engage with AHSN colleagues and stakeholders to plan project​

  - Plan and recruit resource required to support the project including Communications and engagement plan and risk management

  - Early scoping and engagement

  - Develop Driver Diagram

  - Agree finance plan

  - Develop joint approach to communications with ADASS

- Diagnostic Phase

  - Appraise evidence of literature/intervention/innovations​

  - Deterioration tools for use in LD settings​

  - Alignment with West of England and national work undertaken for family carers training programme for Restore2

  - Map key providers and networks ​

  - Scope and engage potential test bed sites

  - Stakeholder analysis and comms plan including agreed language and easy read materials available where required

  - Survey QI capability/capacity ​

  - Survey safety culture​ through appreciative enquiry

  - Structured appreciative enquiry conversations

  - Survey national AHSN network for identified relevant innovations /interventions with evidence base​

  - Scope NIHR related activities

  - Analyse CQC reports and intelligence regarding patient safety and supported living services

  - Support preparation of test site teams re QI capability and development of governance arrangements

- Testing Phase

  - Conduct place based real world testing of identified interventions

  - Test within rural and urban settings

  - Test using agreed QI methodology – measurement for improvement

  - Utilise rapid tests of change (PDSA cycles)

- Design the delivery

- Share learning

5.1 Funding to AHSN’s

Funding arrangements will be underpinned via a separate Letter of Agreement which sits outside this document.

5.2 AHSN Reporting points

The AHSN’s will provide the following reports and outputs;

- Quarterly progress and assurance report to Midlands Regional Programme Leadership Group

- A report will be produced which will detail objectives informed by the LeDeR project and will summarise the intervention/action plan identifying early adoption sites.

- Dec 2021 – Produce learning from diagnostic phase report sharing any early learning from testing sites to inform annual LEDER report and commissioning cycles for 22/23

- May 2022 - Produce final report to share recommendations regarding proof of value and toolkit to inform implementation and options to scale informed by learning. ​

6.0 ADASS support for this project and key deliverables

East and West Midlands ADASS will work in partnership with the programme, and commit to provide:

- Provide appropriate ADASS capacity to support the programme across the East and West midlands.

- Links to wider regional Sector Led Improvement programmes and specifically regional digital pilot that is commencing for 2021/22 with NHSX and LGA.

- Expertise around social care commissioning and contracting. ​

- Knowledge and experience in relation to the Supported Living ‘market’​.

- Track record of working with people with ‘lived experience’ of Supported Living and active links with people who can contribute.​

- Conduit to local authorities and Directors of Social Services who play a statutory role in this area.​

- Act as subject matter expertise e.g. Supported Living workforce matters, LD & A data and performance.

- Provides support to navigate social care landscape, including terminology and communication and relationships.

6.1 Finance to ADASS

- West Midlands ADASS will receive £30k for their contribution to the project and EM ADASS £20k

7.0 NHSEI (Midlands) region support for this project.

- The NHSEI Midlands are the project sponsor for the programme of work including:

- Initiating the project, galvanizing key stakeholders during the commencement of the programme

- Ensure adequate resources are aligned to the programme (via ADASS through a separate agreement)

- Align the project to existing NHSE/I projects including the existing LeDeR and Health Inequalities work for the region and feed into the national LeDeR programme

- Ensure that there are clear risk management processes in place and that communications are appropriately approved by NHSE/I where required working with national NHSE/I colleagues

- Be the main point of contact for NHSE/I and provide the connection to the NHSE/I national LeDeR team as required

- Provide oversight and leadership as required particularly where there are areas of concern particularly where issues cannot not be resolved within the Programme and act as an escalation point where required

- Approve project approach, methodology and structure

- Ensure oversight and delivery of the programme objectives are delivered to Nationally agreed timescales

- NHSEI (Midlands) regional learning disability and autism programme team will be represented at programme leadership group quarterly meetings and any other relevant stakeholder meetings.

- Total funding for the project has been transferred between NHSEI (Midlands) region and WMADASS under the terms of a separate agreement.

8.0 NHSEI National LeDeR Programme support for this project

The National LeDeR programme have provided funding for the managed via NHSEI (midlands) through a separate agreement.

The national NHSE/I LeDeR team will form part of the overall programme of work and provide senior project sponsor sign off working with NHSE/I Midlands to agree objectives and outcomes.

The National LeDeR programme will be represented at programme leadership group quarterly meetings.

9.0 Communications and publicity

The Programme Manager will lead on the production of communications and engagement plan required to implement and deliver the project (e.g. toolkits, briefings, website information, social media) in collaboration with communication teams from all partners, as well as take the lead role in organizing and hosting events.  This will be drawn from support and expertise from the EM AHSN, WM AHSN and ADASS Communication Teams. Any external communications will be approved by project sponsors before being shared/published.

The Communicatios and Engagement plan will be developed in partnership with key partners including NHSE/I and ADASS to ensure messages are clear, concise and in accessible language across both health and social care but also that consideration is given to materials being developed in easy read.

All initial announcements and other communications are to be considered under embargo until the corresponding agreements referenced in section 4.0 are in place between the relevant delivery partners.

All parties will want to publicly speak about the project, for example in the form of social media, newsletters, or press releases. For such public communications:

- The parties will agree key messages and core texts about the project that can be used by all parties throughout and after the project.

- For other substantive communication (such as blogs, media releases, newsletters, or case studies), the parties commit to making each other aware of the planned communication with an opportunity to comment and request changes.

- All stakeholder communication leads will be involved in signing off proactive (and where deadlines allow) reactive communications.

For Freedom of Information requests pertaining to the project to any partner, their existing FoI approach will apply (including exceptions where appropriate, such as commercial confidentiality).

Partners agree to inform one another of relevant FoI requests received relating to the project.

All parties will remain available for sharing learning and insights from the project, for up to 6 months after the project close (for example through workshops, or presentations), for the purpose of knowledge sharing with Local Authorities, the NHS or academia.

All communication related materials, and distribution channels will be formally agreed with NHSE&I communications team prior to dissemination. (this will be via Fiona Ireson, Senior Communications Manager, NHS England and NHS Improvement).

10.0 Governance

All parties undertake to provide information and appropriate representatives to meet with one another as required in order to facilitate the delivery of the project. Where required, the appropriate mechanisms and agreements will be put in place via liaison by the appropriate parties and accompanied with the relevant documentation.

The programme leadership group will meet bi-monthly for the duration of the project and will require representation from East and West Midlands AHSNs, East and West Midlands ADASS and NHSEI Midlands Region to be quorate. Leadership Group meetings will be co-chaired by Patient Safety Leads from the East and West Midlands AHSN’s, deputised by the Programme Manager.

The programme leadership group will receive quarterly assurance reports and progress updates from delivery partners regional steering groups (AHSN and ADASS).

Regional Steering groups will oversee the test sites within East and West Midlands.

Regional Steering groups will ensure all test sites have planned appropriate clinical and information governance arrangements required to ensure safety of the public and of information.

In addition, specific governance arrangements including the reporting requirements, decision making, areas of responsibility and corresponding structures relating to the delivery of the project will be described in the agreements between parties referenced in section 4.0.

10.1 Data sharing Agreements and Data Controller

It is anticipated that this project is likely to use sensitive, confidential (organisational or patient derived data) or personal data for the purposes of evaluation or understanding the impact of the project, and therefore will require appropriate data sharing arrangements to be in place. Any such data will be subject to separate Data Sharing Agreements between participating organisations and these being in place prior to any such data being shared. Data controllers also identified as a part of these

11.0 Clinical Governance

Given the scope and interdependencies of this pilot, patient safety is of the highest importance. We expect areas to continue using locality level incident reporting procedures to capture any patient safety issues. We expect that the risk of these incidents occurring and responsibility to report and address any incidents that do occur to continue to sit with the sites, including those that would usually require investigation or review and remedial actions.

The AHSN’s are not accountable for clinical responsibility or liability, however risks identified in advance will be managed via a risk register and attempts at mitigation via the local steering groups and leadership group and system stakeholders.

Risk management and reporting will be a key element of this project to ensure no clinical risk to service users.

12.0 Confidentiality

All parties reaffirm in any collaboration between them they will adhere to all statutory requirements relating to confidentiality as they relate to identifiable information or the sharing of data.

13.0 Dispute resolution

Every effort will be made to resolve disputes through the established governance structures referenced in the agreements between parties referenced section 4.0. Any unresolved issues will be escalated to the appropriate Executive Officer / Director within each party.  Where there is a deciding vote on a matter, this will be determined by the commissioner i.e. NHSEI.

14.0 Termination

If at any time any Party or Parties does wish to terminate the WOWWOW then it can be terminated by notice in writing. In any event the WOWWOW will terminate on completion of the project, as agreed in the detailed project plans referenced in section 4.0, or no later than 31st May 2022

15.0 Legal Status

This WOWWOW is a non-binding agreement between the parties. It has no legal standing, and neither party will seek redress through any legal process.

16.0 Duration

The duration of the planned project is anticipated to be 01/04/2021 to 31/05/2022

17.0 Contact Information

The primary contacts for this work in the respective parties are as follows:

Eddie Alder, Head of Patient Safety

East Midlands Academic Health Science Network

C Floor, Institute of Mental Health,

University of Nottingham Innovation Park

Triumph Road

NG7 2TU

Tel: 07976 625678

Email: eddie.alder@nottingham.ac.uk

Jodie Mazur, Head of Patient Safety

West Midlands Academic Health Science Network

Office 12, Ground Floor, Institute of Translational Medicine

Heritage Building (Queen Elizabeth Hospital)

Mindelsohn Way, Edgbaston, Birmingham, B15 2TH

Tel: 0777 070 4009

Email: Jodie.mazur@wmahsn.org

Pete Jackson, Improvement Director

West Midlands ADASS

Tel:

Email: Pete.Jackson@wm-adass.org.uk

Sue Wilson, East Midlands Regional Improvement Programme Manager East Midlands ADASS

Tel: 07843 582304

Email: sue.wilson2@nottscc.gov.uk

Robert Ferris-Rodgers,

Deputy Director of Transformation

Midlands Regional Learning Disabilities and Autism Programme Lead

NHS England and NHS Improvement – Midlands

Tel: 07710152632

Email: r.ferris-rogers@nhs.net

Roxanna Modiri,

Senior Healthcare Consultant

Working on behalf of Midlands Regional Learning Disabilities and Autism Programme Lead

NHS England and NHS Improvement – Midlands

Tel: 07980699994

Email: roxanna.modiri2@nhs.net

Dr Emily Handley-Cole

National Premature Mortality Implementation Lead

Learning Disability Mortality Review (LeDeR) Programme

NHS England 
Skipton House, 80 London Rd, SE1 6LH

Tel: 07730379730
Email: Emily.handley-cole@nhs.net

[INSERT FULL CONTACT INFORMATION FOR OPERATIONAL LEAD FOR EACH PARTY ORGANISATION]

This Memorandum of Understanding is made this …. day of XXXXX 2021

Signed for and on behalf of Nottingham University Hospitals NHS Trust / East Midlands Academic Health Science Network:

Signed: ____________________________________	Date: ________________

Print name: Eddie Alder

Position:     Head of Patient Safety, EMAHSN

Signed for and on behalf of West Midlands Academic Health Science Network:

Signed: ____________________________________	Date: ________________

Print name: Jodie Mazur

Position:      Patient Safety Collaborative Lead, WMAHSN

Signed for and on behalf of West Midlands ADASS

Signed: ____________________________________	Date: ________________

Print name:    Pete Jackson

Position:        Improvement Director

Signed for and on behalf of East Midlands ADASS

Signed: ____________________________________	Date: ________________

Print name: Sue Wilson

Position: East Midlands Regional Improvement Programme Manager East Midlands ADASS

Signed for and on behalf of NHS England and Improvement (Midlands)

Signed: ____________________________________	Date: ________________

Print name: Roger Ferris-Roberts

Position: Deputy Director of Transformation, Midlands Regional Learning Disabilities and Autism Programme Director

Signed for and on behalf of National LeDeR Programme, NHS England and Improvement

Signed: ____________________________________	Date: ________________

Print name: Dr Emily Handley-Cole

Position: National Premature Mortality Implementation Lead, Learning Disability Mortality Review (LeDeR) Programme. NHS England Skipton House, 80 London Rd, SE1 6LH

Appendix A – Background Information – 1. EMAHSN Initial Expression of Interest Form

Managing Deterioration in Supported Living for people with a Learning Disability – Project Outline

Extensive work is underway in local areas across England to improve the management of deterioration amongst people with a Learning Disability living in care homes. However, this cohort only captures 11% of people with a Learning Disability, leaving those with potentially less social care support at a higher level of vulnerability to poorly managed deterioration.

This work aims to undertake an at-pace pilot of an approach to managing deterioration amongst people with a learning disability living in supported living settings. The aim is to develop a strong evidence-based product/methodology/tool that can be scaled up and rolled out nationally. (i.e. a clearly defined, replicable model with a “how to” guide to reduce unnecessary duplication of work when it is rolled out).

Supported living is varied in terms of the level of support provided, with some people living relatively independently in their own homes with a few hours of outreach support per week, whilst others live either alone or with other service users with 24hr staff support.

The LeDeR programme and longstanding reports provide evidence that the signs of health deterioration are not always detected promptly by carers and furthermore that concerns expressed by carers to health professionals are not always taken seriously or responded to in ways that maximise the potential for good health outcomes. As such, people with a Learning Disability die prematurely with conditions that could have been prevented or amenable to treatment, with commonly occurring causes of death including pneumonia, aspiration pneumonia, sepsis, ischaemic heart disease and epilepsy. There are also a concerning number of deaths due to constipation.

The work will be framed within the PIER model of deterioration management, to ensure that consideration is given to where an intervention could be most impactful, i.e Prevention, Identification, Escalation or Response (or a combination of these).

There would likely be merit in working alongside ADASS, as the roll out will be dependent on engagement with the social care sector and collaboration between health and social care.

The preliminary stage of this work will involve defining the scope of the pilot, including but not limited to consideration of the following questions:

- Will all types of supported living/levels of support be included or one end of the spectrum?

- Could assistive technologies play a role and, if so, which technologies are available that could be considered for use within this work (e.g. “Cradle”, “Oxihealth”, “e-hospital hotpod” and others).

- How will impact be measured? (This could include metrics such as ambulance data, A & E attendance rates, hospital conveyance rates, hospital admission rates, self-reported outcomes, levels of staff and/or patient confidence etc.)

- What are the current baselines? Is there regional variance or any areas of excellence that could be learned from?

- Which geographical area(s) will the pilot be in (consider urban & rural areas for comparison)

- Whether the pilot would span all clinical conditions or focus on a specific condition or conditions.

- Which other services would need targeting within the pilot (e.g. is it just supported living, or would community teams/GPs/emergency services also need engaging?)

- Which level(s) of the PIER model should be targeted? (e.g. is the critical issue improving communication between carers and healthcare professionals or does recognition of deterioration also need improving?)

By May 2021, the testbed work should be evidenced along with a report on the approach recommend to be adopted and in what circumstances. This will provide the required evidence base to inform a national managing deterioration strategy for people with a learning disability.

# Appendix B- Prevention Identification Escalation and Response (PIER) framework

# [INSERT PIER FRAMEWORK)

# Appendix C – EMAHSN Offer of Support

# [INSERT EMAHSN OFFER OF SUPPORT LETTER]