## RISKS & ISSUES
|  | RISK & ISSUES |  |  |  | Instruction
PROJECT RISKS AND ISSUES |  |  |  | PROJECT: | Managing Deterioration for People with LD Living in Supported Living Settings | Impact guidance | L | The situation would not have an obvious effect on the objectives, budget and timescales of the project. It could cause some nuisance to some stakeholders with a minimum impact on engagement levels.
[7 empty] | M | The situation may impact on the project delivery, objectives, budget, timescales and/or engagement/satisfaction of stakeholders. Mitigating actions are needed.
|  |  |  | LEAD: | Samson Ifere |  | H | The impact on the delivery, objectives, budget, timescales and engagement will require escalation to decide on substantial changes to the project.
Ref. | Details | Date identified | Risk (R) Issue (I) | Impact | Actions | Owners | Due date | Status / Result | Comment
1 | Potential for Providers and families to be slow with engaging with questionnaire survey as completion would be online leading to low response rate across the regions |  | I | M | Ensure communication routes are robust and reach the target audience. Project delivery group places more of a focus on the Semi Structured Interviews and aim for a better response rate | Project Group |  | Active
2 | Impact of the pressures faced by Health and Social Care Organisations and SL providers and families due to differing internal priorities, staff absences e.g. christmas leave, term holiday, winter pressures, rising covid rates etc., might impact upon engagement with the pilot. |  | R | M | Continute to monitor changes within the environment Appointment of ADASS Project Team across EM and WM to work alongside working group to facilitate conversations and align to sector Early engagement with commissioning colleagues across agreed regions and identifiying key players. Adjust scale of test sites/groups to ensure best support given and rapid cycles of change are implemented Extend test cycle where/if necessary - inform leader group as appropriate working closely with LA to identify providers who are willing and able to commit to the programme, keeping in mind developing pressures as the project goes on. | Project Group |  | Active
3 | Timescales as we progress from planning into testing - delays in milestone tasks could potentially have an impact on project delivery |  | R | L | maintain flex with training dates, pdsa cycling etc. continue to engage with sector to gain feedback relative to system pressures additional support from project officers and wider AHSN teams to facilitate for undertaking tasks in parallel | Project Group |  | Controlled
4 | Working across multiple organisations presents bureaucratic and cultural challenges due to use of different languages/terminologies etc. |  | R | M | Establish Project Delivery Group representing core working group of Social and Health working groups Ways of Working Document Developed glossary of terminology used in Social Care which might defer establishing esclation pathway/route as part of overall project delivery group and externally | Project Group |  | Controlled | Tripple Loop learning to be reflected in report Establishing reflective sessions within core project
5 | Data - access to robust and accurate data which would inform approach might be limited |  | I | M | Process and outcome measures put in place to track progress and be refleacted via quality improvement and PDSA cycles. Safety cross developed and in use by SL providers through testing, with planned alignment to GP audits. | Project Group |  | Controlled
7 | Current pressures being faced by primary care could present a challenge with engagement and operational delivery requirements due to increasing patient demand, and dropping levels of demand as a result of fatigue due to C-19 Pandemic |  | R | H | Ensure dependence/reliance on Primary Care i.e. General Pracitce is limited to only as necessary as possible Identify LD leads within General Practice (where available) as this programme will align with their current ambitions Supply support staff to conduct audits/surveys on behalf of the Surgeries where/if possible Ensure communication with this group is targetted and Engage with PCN/CCG's/GP Federation etc. to faciliate/broker conversations where possible/necessary | Project Group |  | Active
8 | Comms support lagging in terms of delivery of comms related tasks |  | I | L | Weekly meetings put in place by comms group, with action log and associated comms related activities identified and addressed. Draft comms strategy completed with SMART objectives and associated metrics of measure. To be signed off. | Project Group |  | Controlled
9 | Sharing Documents - cloud based storage |  | I | M | Issues have been experienced with regards sharing documents using Microsoft sharepoint. Google Drive has been used however this also presents some issues with certain firewalls/access rights. This has led to some delays in disseminating information to stakeholders involved | Project Group |  | Controlled