## Slide 1: Managing deterioration Safety Improvement Programme April 2022 - June 2023) End of programme report
July 2024

## Slide 2: Introduction
‘Managing deterioration’ refers to spotting that a person’s physical condition is worsening and responding appropriately to support best health outcomes, keep them safe and provide a positive experience of care.'
East Midlands Patient Safety Collaborative (PSC) is delivering the Managing Deterioration Safety Improvement Programme (ManDetSIP), commissioned by NHS England. The programme is part of the National Patient Safety Improvement Programme and is strongly aligned to the NHS Patient Safety Strategy.
National aims
The programme aimed to reduce deterioration associated harm by increasing the use of a PIER framework (prevention, identification, escalation and response) to address physical deterioration through better system co-ordination, and as part of safe and reliable pathways across health and social care:
Prevention – Enhancing and maintaining health and well-being to ensure best health.
Identification – Identifying when someone becomes unwell and responding as needed.
Escalation – Communicating people’s needs when they become unwell to access the right care from the right people.
Response – Responding in a timely and appropriate way when somebody’s health deteriorates.

## Slide 3: Introduction
Key ambitions
Adoption of deterioration management tools (RESTORE2/RESTORE2mini or equivalent) in at least 30% of care homes (including homes caring for people with learning disability, autism and mental ill-health) by the end of March 2023.
Support 50% of care homes to receive training in a deterioration management tool.

## Slide 4: Actions taken
Providing a bespoke 'Train the Trainer' package on managing deterioration to Integrated Care Boards, enabling nominated teams to train care homes, and support them with embedding and sustainability.
Developing a free online training package to support training for care homes - REACTO Deterioration
Delivering quarterly Connecting Together webinars for care home staff on key learning topics such as frailty, which include hearing from care homes who can highlight and share best practice.
Extended the training to primary care and those working with care homes as well as to Domiciliary Care workers, who provide key care to people in their own homes.
Celebrate and share best practice through East Midlands Care Awards.
Signposting and supporting quality improvement methodology.

## Slide 5: Impacts and outcomes
Provided training to 1,576 people from 370 organisations (Care homes trained: 283 / Care home staff trained:1312. Home care orgs: 33 / Home care staff trained:176)
A care conference and awards event attracted 200 attendees and 35 exhibitors. This year the awards were opened to domiciliary care as well as to care homes, as the programme’s reach extended.
Working with The University of Nottingham Pharmacy School we piloted a project to place students at Ashfields Care Home, Derbyshire to support care home staff to use the managing deterioration tools and learn about medicines management in care homes. Feedback was positive and we are supporting the University of Nottingham to expand the pilot to place 200 students in East Midlands care homes from September 2024.

## Slide 6: Number of people and organisations reached
Activity | Total number of participants | Time (each session) | Total time | No. of organisations | Types of organisations
Managing deterioration PIER training x 14 | 536 | 1.45hrs | 24.5hrs | 210 | Care homes and home care providers
Managing deterioration PIER training for learning disabilities x 6 | 73 | 1.45hrs | 10.5hrs | 46 | Learning disability care homes
Skills for Care local training x 3 | 30 | 2.00hrs | 6.00hrs |  | Care homes, home care, Skills for Care local teams
Connecting Together meeting x 2 | 146 | 1.5hrs | 4.00hrs |  | ICB, PCN, care homes, home care
PCN SBARD training x 3 | 20 | 1.00hrs | 3.00hrs |  | Notts PCN staff
Care conference | 118 | 7.00hrs | 7.00hrs | 59 | Care homes, home care, ICB EHCH and Ageing Well teams, Adult Social care
Northants virtual training x 2 | 625 | 1.45hrs | 3.50hrs | 134 | Northants care homes, home care, ICB teams
Northants in person training | 25 | 2.00hrs | 2.00hrs | 23 | Northants care homes, home care, ICB teams

## Slide 7
Deterioration tools, why use them?
Training on spotting early signs of deterioration allows prompt escalation & response via primary care
Reducing avoidable conveyances to hospitals and
inpatient stays with the associated
deconditioning of residents.
Extend training to Domiciliary Care and GP-registered carers to keep people safe in their own homes

## Slide 8
System
Benefits
Increased staff confidence with care staff feeling better able to advocate for their residents and present concerns professionally and confidently to clinicians
Increased staff job satisfaction and skill set improving retention
System cost savings with reduced 999 calls and ambulance call outs, conveyances and hospital stays
Reduction in incidents including safeguarding referrals – saving staff time as well as improving patient safety
CQC – evidencing use of a managing deterioration tool is viewed very positively by CQC
Financial savings including from staff time when having to accompany a resident to hospital
More residents able to stay in their preferred place of care
Extending training to Domiciliary care and supported living supports strategy to keep people safe in their own home
1.
2.
4.
5.
7.
6.
8.
3.
Notes: When discussing drop in some of the feedback from care staff "

## Slide 9
Benefits to Primary Care
Time released back to primary care teams including GP's through use of SBARD in MDT and care home rounds
Builds relationships between NHS and social care with clearer, concise
communication
Early escalation to primary care reduces urgent GP visits to care homes

## Slide 10: Survey Feedback
Chart: How confident are you with identifying soft signs?
| 0. Not Confident at All | 1. Not Confident | 2. Limited Confidence | 3. Somewhat Confident | 4. Confident | 5. Very Confident
Pre-training | 0.23821 | 0.1737 | 0.12407 | 0.20844 | 0.16625 | 0.08933
Post-training | 0 | 0 | 0.0024038 | 0.021635 | 0.26442 | 0.71154
Chart: How confident are you with escalating concerns about a resident to others outside of the care home?
| 0. Not Confident at All | 1. Not Confident | 2. Limited Confidence | 3. Somewhat Confident | 4. Confident | 5. Very Confident
Pre-training | 0.031785 | 0.0489 | 0.04401 | 0.10513 | 0.25672 | 0.51345
Post-training | 0 | 0 | 0.0049383 | 0.014815 | 0.2642 | 0.71605

## Slide 11
Potential Impacts
The modelled West Midlands data estimated that adopting deterioration management tools had the potential cumulative benefits:
Time period: Jan 2021 to Sep 2022
Estimated effect of adopting the intervention on care homes
Estimates based on comparing trends between intervention and control groups
The evidence suggests the right patients are being conveyed (reduction in avoidable admissions). This can be monitored over time, alongside the results of the modelling, with further analysis.
Reduction in
emergency admissions
Reduction in
total length of stay (bed days)
-3,232
(~4% reduction*)
-34,900
(~5% reduction*)
Reduction in 999 calls
-2,236
(~1% reduction*)

## Slide 12
SBARD Feedback
Managing deterioration/RESTORE2 training should be mandatory for care homes, why not yearly training? The more we use this tool, the more we can improve our practice! The trainings are brilliant, and SBARD tool is really supportive.
I use with handovers to ambulance transfers for critical residents who need admitting.
Just started to use SBARD and it has helped effective communication and helped getting the right information to the right person quickly.
All 38 of our care homes are now trained and using SBARD, staff say they feel more listened to and their knowledge of the residents acknowledged more. Several good examples across the company of where residents lives have been enhanced by immediate reaction using soft signs and SBARD-empowering.
We are using SBARD in our weekly ward rounds now, so we are able to identify the needs and changes in a resident.
SBARD is especially useful when shifts change, so the next team knows exactly what was happening with the resident. This ensures we deliver the best care possible to our residents.
During a shift there was a sudden health issue with one of our residents. This time we used SBARD - gave more confidence for handling the situation.

## Slide 13
Soft Signs and SBARD Case Study – Ashfields Care home
We find that a lot of staff can help fill out a SBARD form. The night staff, if they notice changes overnight start to fill in an SBARD for us to deal with in the morning (non-life threatening).
We find staff are putting more information on the SBARD form as it’s there and tells them what they need to be writing. It helps with shift handovers as we have all the information we need.
We also scan all the SBARD forms onto people’s care plans, so we can use them. We get the GP to fill out the bottom bit (decision section) with the decision that they’ve made and sign it, so if they’ve decided to start somebody on Antibiotics, but the chemist has still not received the prescription, we’ve got the SBARD form to prove that was what was said at that time. So, it just keeps us safe as well and it helps protect everybody.
It also gets the staff to look back at past medical histories of the residents as well, so it gives them up-to-date knowledge of what’s going on with the residents because, with all the will in the world, you can’t remember what’s happening with everybody and what everybody’s medical history is, but this is helping prompt people on what to do. The seniors have found it very helpful because some staff aren’t confident and before SBARD were not quite sure on how to write things down or how to explain things.

## Slide 14
Soft Signs and SBARD Case Study – Rathgar Care home
We had a lady who was poorly with a chest infection and had been put on antibiotics. I noticed one day when I came on shift that her behaviour had changed (soft signs) She was becoming more agitated, she was fighting us and screaming in pain.
We did a NEWS2 and she scored low but I knew from her behaviour that something wasn’t right. She started refusing food and drink. I escalated this (using SBARD) and the GP came to visit but agreed that although her NEWS2 was still low something wasn’t right and recommended calling an ambulance.
When the ambulance arrived,
they did a NEWS2 and said she wasn’t presenting high. I went through the SBARD again with them, what we thought was happening and our recommendation. They didn’t want to listen or take her to the hospital, but I gave them the SBARD info again along with the soft signs and said this lady deserves a chance to try to get fit and well.
I kept pushing as I was the lady’s voice and said the GP agreed this lady should go to hospital. As Carers we know our residents and we know when something isn’t right.
The lady went to hospital where she was diagnosed with developing sepsis

## Slide 15: Resources
Use the links below to find out more
Support for care homes
Care awards and Conference
Signposting and supporting quality improvement methodology
PSC impact report (Summer 2023)
Managing Deterioration section of HIEM 2023-24 report
REACTTO Deterioration

## Slide 16: Next steps
In 2024-2025, the Managing Deterioration programme focuses on two key areas;
Supporting designated pilot sites to implement Martha’s Rule to help patients and families to escalate concerns and request an urgent review if their condition deteriorates.
Implement a wider integrated national programme to improve the management of deterioration using the PIER (Prevent, Identify, Escalate and Respond to physical deterioration) Toolkit.

## Slide 17: Further information
Email: healthinnovation-em@nottingham.ac.uk
Web: healthinnovation-em.org.uk
X: @Healthinn_em
Linkedin: Health Innovation East Midlands
Sign up to our newsletters: healthinnovation-em.org.uk/updates
Register for our Innovation Insight webinars on a range of topics